External review of (AGENCY) against the ESG
TERMS OF REFERENCE
The present Terms of Reference were agreed between XX (applicant), YY (coordinator) and EQAR.
# 1. Background
[You can add a paragraph with basic information about the reviewed agency here. When doing so, please do not use value statements, such as “the agency has gained financial and administrative independence…”, as this will be reviewed during the external review process.]
Either:
XX has been registered on the European Quality Assurance Register for Higher Education (EQAR) since … and is applying for renewal of EQAR registration
Or:
XX is applying for EQAR registration for the first time.
# 2. Purpose and scope of the evaluation
This review will evaluate the extent to which XX fulfils the requirements of the Standards and Guidelines for Quality Assurance in the European Higher Education Area (ESG). Consequently, the review will provide information to EQAR to support XX's application.
## 2.1 Activities of XX within the scope of the ESG
This review will analyse all activities of XX that are within the scope of the ESG, i.e. reviews, audits, evaluations or accreditation of higher education institutions or programmes that relate to teaching and learning (and their relevant links to research and innovation). This is independent of whether the activities are carried out within or outside the EHEA and whether they are obligatory or voluntary in nature.
The following activities of XX have to be addressed in the external review:
[Please list all your external quality assurance activities that fall within the scope of the ESG (see also chapter 4 of EQAR’s Use and Interpretation of the ESG). Note that EQAR might still edit the list before the Terms of Reference are finalised.
All these activities will be included on the agency's profile on the EQAR website and linked to DEQAR database. NB: The agency may not upload reports from other activities to DEQAR.
# 3. The review process
The review will be conducted in line with the requirements of the EQAR Procedures for Applications.
The evaluation procedure consists of the following steps:
- Formulation of the draft Terms of Reference for the review between XX and YY;
- Agreement on the Terms of Reference by EQAR;
- Nomination and appointment of the review panel by YY;
- Self-assessment by XX including the preparation and publication of a self-assessment report;
- A site visit by the review panel to XX;
- Preparation and completion of the final review report by the review panel;
- Analysis of the final review report and decision-making by the EQAR Register Committee.
## 3.1 Independence of the review coordinator
YY has not provided remunerated (e.g. consultancy) or unremunerated services to XX during the past 5 years, and conversely XX has not provided any remunerated or unremunerated services to YY.
(if the review is coordinated by another agency) Both YY and XX committed themselves not to be reviewed in the next 5 years by the agency for which it coordinates the review.
## 3.2 Nomination and appointment of the review team members
The review panel consists of N (at least 4) members:
(list profiles of members)
(As a minimum, panel needs to include an academic employed by a higher education institution and a student member; at least one member needs to be from another country.)
(Describe how the panel will be recruited, and which specific roles exist, e.g. chair or secretary.)
YY will ensure that all panel members have either completed a formal training for agency reviews against the ESG 2015, or have participated in at least two reviews of quality assurance agency against the ESG that were accepted to support an application to EQAR.YY ensures that experts are selected from a wide variety of different backgrounds and at least one expert from a different country.
The panel will be supported by the YY (Staff member) who will monitor the integrity of the process and ensure that EQAR's requirements are met. (Describe the role and responsibilities of YY staff involved.)
YY will provide XX with the list of suggested experts and their respective curricula vitarum to establish that there are no known conflicts of interest. The coordinator does not select experts who have been previously involved in providing services to the applicant quality assurance agency or otherwise have a real or apparent conflict of interest. The experts will have to sign a non-conflict of interest statement as regards the XX review, covering at least the cases of interest defined in the EQAR Code of Conduct.
Once appointed, YY will inform EQAR about the appointed panel members.

## 3.3 Self-assessment by XX, including the preparation of a self-assessment report
XX is responsible for the execution and organisation of its own self-assessment process and shall take into account the following guidance:
- Self-assessment includes all relevant internal and external stakeholders;
- The self-evaluation report shall reflect on the applicant’s compliance with each of the ESG in parts 2 and 3. The report is a critical reflection on the activities, strengths and weaknesses of the applicant and the added value they provide for quality improvement of higher education institutions.
- The self-assessment report is broken down by the topics of the review and is expected to contain, among others: a brief description of the national HE and QA system; background description of the current situation of the Agency; an analysis and appraisal of the current situation; proposals for improvement and measures already planned; a SWOT analysis; each criterion (ESG part 2 and 3) addressed individually, and considerations of how the agency has addressed the recommendations as noted in the previous EQAR Register Committee decision of inclusion/renewal (if applicable).
- All of the above listed external QA activities (whether within their national jurisdiction or outside of it, and whether obligatory or voluntary) will be described and their compliance with the ESG analysed.
- The report is well-structured, concise and comprehensively prepared. It clearly demonstrates the extent to which XX fulfils its tasks of external quality assurance and meets the ESG and thus the requirements for EQAR registration.
- (Describe any scrutiny of the SAR by YY, if applicable)
- The report is submitted to the review panel N months/weeks prior to the site visit.
## 3.4 A site visit by the review panel
The review panel will draft a proposal of the site visit schedule which shall be submitted to the agency at least N weeks/months before the planned dates of the visit. The schedule is to include an indicative timetable of the meetings and other exercises to be undertaken by the review panel during the site visit, the duration of which is usually N (typically 2 to 4) days. The approved schedule shall be given to XX at least one month before the site visit, in order to properly organise the requested interviews.
The site visit will close with a final de-briefing meeting outlining the panel’s overall impressions but not its judgement on the ESG compliance of the agency.
## 3.5 Preparation and completion of the final review report
The review report will be drafted in consultation with all review panel members and correspond to the purpose and scope of the review as defined under articles 2 and 2.1. In particular, it will provide a clear rationale for its findings concerning each ESG. When preparing the report, the review panel should bear in mind the EQAR Policy on the Use and Interpretation of the ESG to ensure that the report will contain sufficient information for the Register Committee for application to EQAR[1].
[1] See here: https://www.eqar.eu/assets/uploads/2018/04/UseAndInterpretationOfTheESGv2.0-2015.pdf
The external report will reflect reality at the time of review.
A draft will first be submitted to XX usually within N weeks of the site visit for comment on factual accuracy. If XX chooses to provide a position statement in reference to the draft report, it will be submitted to the chair of the review panel within N weeks after the receipt of the draft report.
Thereafter, the review panel will take into account the statement by XX and submit the document to YY and EQAR. All panel will sign off on the final version of the external review report. YY will provide to XX the Declaration of Honour together with the final report.
The report is to be finalised within N weeks/months of the site visit and will normally not exceed 50 pages in length.
# 4. Publication of the report
XX will receive the expert panel’s report and publish it on its website. The report will also be published on the EQAR website together with the decision on registration, regardless of the outcome.
# 5. Decision-making on EQAR registration
The agency will submit the review report via email to EQAR (in case of renewals to be added ‘before expiry of the agency’s registration on EQAR’). The agency will also include its self-assessment report (in a PDF format), the Declaration of Honour and the full curriculum vitae (CVs) of all review panel members. In addition, XX may provide any other relevant documents to the application (i.e. annexes, statement to the review report).
EQAR is expected to consider the review report and the agency’s application at its Register Committee meeting in (add month, year).
# 6. Indicative schedule of the review
Agreement on Terms of Reference	Month/year
Appointment of review panel members	Month/year
Self-assessment completed	Month/year
Preparation of site visit schedule and indicative timetable	Month/year
Briefing of review panel members	Month/year
Review panel site visit	Month/year
Draft review report	Month/year
Statement of XX to review panel (if applicable)	Month/year
Submission of final report to YY and EQAR	Month/year
EQAR Register Committee meeting and decision on the application by XX	Month/year